# NOST-Bench + RIFT-Net/RIFT-Mamba Operations Annex v2.1

Runbook, SOP, gate execution, artifact governance and implementation discipline

Prepared for research planning and controlled implementation

2026-04-24

Table of Contents

# 1	NOST-Bench + RIFT-Net/RIFT-Mamba Operations Annex v2.1

## 1.1	Tuyên bố sử dụng

Tài liệu này là bản vận hành bổ sung cho hai tài liệu chính:

- NOST_Bench_RIFTNet_RIFTMamba_Proposal_v2_1_2026-04-24.docx - giữ định vị khoa học, câu hỏi nghiên cứu, đóng góp, kịch bản công bố và claim boundary.

- NOST_Bench_RIFTNet_RIFTMamba_Technical_Framework_v2_1_2026-04-24.docx - giữ blueprint kỹ thuật, kiến trúc, metrics, controls, schemas, policy tests và model family.

Operations Annex này không thay thế Proposal hoặc Technical Framework. Vai trò của nó là biến hai tài liệu đó thành một runbook có thể thực thi: ai làm gì, chạy theo thứ tự nào, artifact nào phải có, điều kiện go/no-go là gì, và khi có blocker thì phải xử lý ra sao.

Nguyên tắc quan trọng:

- Không mở claim mới.

- Không đổi headline claim, comparator inventory, latent capacity mainline, gate semantics hoặc threshold đã khóa.

- Mọi chi tiết vận hành phải làm giảm degrees of freedom, không tạo thêm freedom hậu nghiệm.

- Nếu xung đột: Technical Framework thắng về execution rule; Proposal thắng về scientific positioning; Operations Annex chỉ làm rõ cách vận hành.

- Không có substantive/claim-bearing run nếu chưa qua Gate 0, Gate 1, Gate 2, Gate 2.5 và policy tests tương ứng.

## 1.2	Executive Summary

NOST-Bench là benchmark control-first cho scalp-iEEG transfer. RIFT-Net Lite là model primary; RIFT-Mamba, Riemannian và Bridge là extensions có điều kiện. Operations Annex v2.1 khóa quy trình vận hành từ lúc chuẩn bị dữ liệu đến claim-state closeout.

Trạng thái khởi đầu đúng của dự án:

- Framework/proposal: đã đủ để triển khai có kiểm soát.

- Empirical claim: chưa được mở.

- Current operational stance: NO-GO for claim-bearing model cho đến khi signal-level Gate 0, Gate 1 decision memo, Gate 2 synthetic validation, Gate 2.5 prereg bundle và policy tests pass.

Mục tiêu vận hành:

- Chuyển proposal và framework thành chuỗi run có thể audit.

- Khóa source of truth, artifact, pass/fail rule và revision policy.

- Ngăn các lỗi thường gặp: leakage, post-hoc tuning, weak controls, gate circularity, bridge provenance ambiguity, model over-engineering và claim drift.

- Đảm bảo nếu kết quả dương tính, âm tính hoặc data blocked thì đều có đường báo cáo hợp lệ.

# 2	1. Document Map and Source-of-Truth Hierarchy

## 2.1	1.1 Ba lớp tài liệu

| Lớp | Tài liệu | Vai trò |
| --- | --- | --- |
| Scientific layer | Proposal v2.1 | Câu hỏi nghiên cứu, motivation, contribution, hypothesis, expected scenarios, publication framing. |
| Technical layer | Technical Framework v2.1 | Kiến trúc pipeline, model family, metrics, controls, schemas, tests, risk mitigation. |
| Operations layer | Operations Annex v2.1 | SOP, runbook, RACI, gate checklist, execution sequence, artifact handoff, escalation. |

## 2.2	1.2 Quy tắc ưu tiên khi có mâu thuẫn

| Tình huống | Tài liệu ưu tiên | Hành động |
| --- | --- | --- |
| Claim scope, contribution, paper positioning | Proposal | Giữ benchmark-first, RIFT-Net Lite primary, fail-safe scenarios. |
| Split, leakage, test-time input, metric/claim rule | Technical Framework | Không được nới hoặc diễn giải lại trong operations. |
| Tên file artifact, SOP, ai review, thứ tự chạy | Operations Annex | Được làm rõ miễn không đổi claim/technical rule. |
| Threshold sau khi đã freeze | Prereg bundle / threshold registry | Không sửa trong runtime; mọi thay đổi cần revision log và re-freeze. |
| Dữ liệu thật khác metadata public | Signal-level Gate 0 artifact | Local snapshot audit thắng public metadata. |

## 2.3	1.3 Definition of Done vận hành

Một phase chỉ được xem là hoàn tất khi có đủ:

- Artifact bắt buộc theo phase.

- Schema validation pass.

- Policy tests liên quan pass.

- Reviewer ký hoặc ghi nhận review status.

- claim_state.json hoặc phase summary ghi rõ trạng thái.

- Không có blocker chưa phân loại.

- Không có override hậu nghiệm theo model results.

# 3	2. Operating Principles

## 3.1	2.1 Nguyên tắc không được vi phạm

- Test-time chỉ được dùng scalp EEG.

- iEEG, beamforming, source, teacher outputs, nuisance metadata và subject identity không được bổ sung inference tại test-time.

- Nested LOSO by subject là primary split cho claim chính.

- Cross-session chỉ là secondary robustness, không dùng để cứu power khi LOSO N thấp.

- Không fit bất cứ thứ gì trên outer-test subject.

- Controls là track chính của benchmark.

- Raw BA không đủ claim.

- CRTG phải có SESOI, bootstrap CI và max-T permutation support.

- Control underpowered không được loại hậu nghiệm; claim phải đóng hoặc rerun tier đã preregistered.

- RIFT-Net Lite là primary model; RIFT-Mamba/Riemannian/Bridge chỉ là conditional extensions.

- Mọi artifact claim-bearing phải hash-linked và có provenance.

- Nếu nghi ngờ leakage hoặc artifact drift, fail-closed.

## 3.2	2.2 Nguyên tắc vận hành thực tế

- Chạy nhỏ trước, khóa lớn sau.

- Chạy Gate trước model.

- Chạy controls trước claim.

- Chạy policy tests trước full LOSO.

- Chạy baseline trước RIFT-Net.

- Chạy RIFT-Net Lite trước RIFT-Mamba.

- Chạy bridge chỉ khi bridge provenance pass.

- Không chỉnh subject list, thresholds, controls, teacher gates hoặc hyperparameter space sau khi thấy kết quả.

# 4	3. Operating State Machine

## 4.1	3.1 Trạng thái dự án

| State | Ý nghĩa | Được phép chạy | Không được phép |
| --- | --- | --- | --- |
| Planning | Docs/spec đang được khóa | Draft docs, schema design, toy logic | Real-data claim |
| Framework-ready | Repo skeleton, tests, configs có thể bắt đầu | Unit tests, smoke tests, synthetic draft | Substantive runs |
| Gate0-partial | Một phần payload đọc được | Pilot feature, one-fold smoke | Claim-bearing LOSO |
| Signal-ready | Gate 0 full pass | Baselines, controls, Gate 1/2/2.5 | Claim nếu prereg chưa lock |
| Freeze-ready | Gate 1/2 ready, thresholds locked | Prereg assembly, final preflight | Post-hoc threshold edit |
| Run-ready | Gate 2.5 prereg bundle locked | Full LOSO baselines/RIFT-Net Lite | Changing source-of-truth silently |
| Claim-evaluable | Full artifacts available | Claim-state closeout | Manual claim without closeout |
| Claim-closed | Blockers remain | Negative finding/reporting | Positive claim |
| Claim-allowed | All rules pass | Controlled positive claim | Claims outside locked endpoint |

## 4.2	3.2 Rule for promotion between states

Promotion between states must be artifact-driven, not narrative-driven.

Example:

Signal-ready != someone says data looks OK.
Signal-ready = signal_manifest + cohort_lock_signal_ready + event_alignment_report + blockers empty.

# 5	4. Roles and RACI

## 5.1	4.1 Core roles

| Role | Responsibility |
| --- | --- |
| Scientific Lead | Giữ claim boundary, approves SESOI, approves decision memo, owns paper positioning. |
| Technical Lead | Owns repo architecture, CLI, tests, CI, code review, reproducibility. |
| Data Governance Lead | Owns Gate 0, materialization, manifest, cohort lock, bridge audit. |
| Benchmark Lead | Owns tracks A-E, baselines, controls, leaderboard, artifact schemas. |
| Modeling Lead | Owns RIFT-Net Lite, extensions, training schedule, ablations. |
| Statistics Lead | Owns SESOI, bootstrap, max-T permutation, influence, calibration. |
| QA/Policy Lead | Owns policy tests, leakage checks, deterministic controls, red-team checklist. |
| Reporting Lead | Owns tables, figures, claim-state closeout, manuscript package. |

## 5.2	4.2 RACI matrix by phase

| Phase | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| Gate 0 | Data Governance Lead | Scientific Lead | Technical Lead, QA Lead | All |
| Gate 1 | Statistics Lead | Scientific Lead | Benchmark Lead, Modeling Lead | All |
| Gate 2 | Statistics Lead | Technical Lead | QA Lead | All |
| Gate 2.5 | Technical Lead | Scientific Lead | All leads | All |
| Baselines | Benchmark Lead | Technical Lead | Stats Lead | Scientific Lead |
| Controls | Benchmark Lead | QA Lead | Stats Lead | Scientific Lead |
| RIFT-Net Lite | Modeling Lead | Technical Lead | QA Lead, Stats Lead | Scientific Lead |
| Extensions | Modeling Lead | Scientific Lead | Benchmark/QA/Stats | All |
| Claim closeout | Reporting Lead | Scientific Lead | Stats, QA, Technical | All |

# 6	5. Repository and Workspace Conventions

## 6.1	5.1 Canonical repository layout

nost_bench/
  configs/
    data/
    preprocess/
    splits/
    benchmark/
    models/
    controls/
    gate1/
    gate2/
    prereg/
  src/
    audit/
    data/
    features/
    splits/
    controls/
    models/
    evaluation/
    benchmark/
    reporting/
  tests/
    unit/
    policy/
    integration/
    evaluation/
  artifacts/
    gate0/
    gate1/
    gate2/
    prereg/
    features/
    baselines/
    controls/
    rift/
    evaluation/
    reports/
  docs/
  notebooks/

## 6.2	5.2 Notebook rule

Notebook chỉ orchestration. Notebook không được là source-of-truth cho:

- scientific logic;

- split construction;

- feature fit scope;

- model/loss implementation;

- metric computation;

- claim-state closeout;

- threshold selection.

Durable logic phải ở src/; configuration phải ở configs/; evidence phải ở artifacts/.

## 6.3	5.3 Run ID convention

Recommended run ID:

YYYYMMDDTHHMMSSZ_<phase>_<short-hash>

Example:

20260424T091500Z_gate0_signal_a1b2c3
20260424T103000Z_baselines_loso_d4e5f6

## 6.4	5.4 Artifact naming convention

| Artifact family | File name |
| --- | --- |
| Gate 0 manifest | signal_manifest.json |
| Cohort lock | cohort_lock_signal_ready.json |
| Gate 1 decision | decision_memo.md |
| SESOI registry | sesoi_registry.yaml |
| Gate 2 synthetic | synthetic_recovery_report.md |
| Prereg | prereg_bundle.json |
| Split | split_manifest.json |
| Feature | feature_manifest.json |
| Controls | control_results.csv |
| CRTG | crtg_bootstrap.json, maxT_permutation.json |
| Closeout | claim_state.json, revision_log.md |

# 7	6. Environment and Runtime SOP

## 7.1	6.1 Supported execution environments

| Environment | Purpose | Notes |
| --- | --- | --- |
| Local CPU | Schema/unit tests, small toy runs, docs checks | No heavy training. |
| Colab T4 | Gate 0 sample/subject audit, baselines, RIFT-Net Lite smoke | Use conservative configs. |
| Colab A100 / cloud GPU | Full LOSO model runs, optional Mamba | Only after prereg lock. |
| CI runner | Unit/policy/schema tests | No raw data required. |

## 7.2	6.2 Environment lock

Before any run-ready stage, create:

environment_lock.yml

Required fields:

python_version: "3.x"
os: "linux/colab/local"
cuda: "version or none"
packages:
  mne: "..."
  mne-bids: "..."
  numpy: "..."
  scipy: "..."
  pandas: "..."
  torch: "..."
  sklearn: "..."
  pyriemann: "..."
  h5py: "..."
  mat73: "..."
reproducibility:
  deterministic_torch: true
  cudnn_benchmark: false
  global_seed: 20260424

## 7.3	6.3 Preflight command sequence

python -m unittest discover -s tests
python -m src.cli smoke --profile t4_safe --config configs/data/snapshot.yaml
python -m src.cli validate_configs --root configs
python -m src.cli validate_schemas --root schemas

Go/no-go:

- If unit/policy/schema tests fail: no Gate or model run.

- If smoke fails: fix environment before data audit.

- If config validation fails: do not patch outputs; patch configs and rerun.

# 8	7. Data Materialization SOP

## 8.1	7.1 Objective

Convert dataset from metadata/pointer-like state into materialized, readable EDF/MAT payloads suitable for signal-level Gate 0.

## 8.2	7.2 Materialization modes

| Mode | Scope | Use case |
| --- | --- | --- |
| metadata | BIDS tree and sidecars only | Initial inventory; no signal claim. |
| sample | one subject/session plus one bridge sample | Reader/parser validation. |
| subjects | selected subjects | Partial Gate 0 and pilot. |
| all | full dataset | Full Gate 0 and cohort lock. |

## 8.3	7.3 Required materialization report

materialization_report.json fields:

{
  "dataset_root": "...",
  "mode": "sample|subjects|all",
  "edf_expected_count": null,
  "edf_materialized_count": null,
  "mat_expected_count": null,
  "mat_materialized_count": null,
  "pointer_like_count": null,
  "failed_files": [],
  "retry_log": [],
  "storage_bytes_required": null,
  "storage_bytes_available": null,
  "status": "metadata_only|partial|complete|blocked"
}

## 8.4	7.4 Go/no-go

| Condition | Decision |
| --- | --- |
| all EDF pointer-like | NO-GO for signal audit |
| some EDF readable | partial Gate 0 allowed |
| EEG/iEEG EDF readable for candidate cohort | full Gate 0 can proceed |
| MAT unreadable but EDF pass | RIFT-Bridge locked; RIFT-Net Lite may proceed after Gate 0 |
| Storage insufficient | block and revise materialization plan |

# 9	8. Gate 0 SOP: Signal Readiness and Cohort Lock

## 9.1	8.1 Goal

Gate 0 answers:

- What exact dataset snapshot is used?

- Which EDF/MAT files are materialized and readable?

- Which subjects/sessions/trials are usable for endpoint 4 vs 8?

- Is bridge/source data usable at trial level?

- What is the primary denominator for LOSO?

## 9.2	8.2 Inputs

- configs/data/snapshot.yaml

- materialized dataset root

- BIDS sidecars/events/channels/electrodes

- EDF readers

- MAT readers: scipy.io, h5py, mat73

- locked audit script

## 9.3	8.3 Execution steps

- Freeze snapshot path and dataset version.

- Hash root files and all raw/derivative files used.

- Detect pointer-like payloads.

- Read EEG EDF and iEEG EDF session by session.

- Parse events and task labels.

- Validate 4-vs-8 trial availability.

- Validate event windows against signal duration.

- Validate sampling frequency and recording type against payload.

- Validate channel and electrode inventory.

- Parse MAT/source derivatives if bridge is requested.

- Verify subject/session/trial-level mapping for bridge.

- Write artifacts.

- Conduct Gate 0 review.

- Lock cohort or block.

## 9.4	8.4 Required outputs

| Output | Required? | Purpose |
| --- | --- | --- |
| signal_manifest.json | Yes | Dataset/file/provenance source of truth. |
| materialization_report.json | Yes | Payload status and failure list. |
| event_signal_alignment_report.json | Yes | Event-to-signal integrity. |
| cohort_lock_signal_ready.json | Yes | N_primary_eligible and exclusions. |
| bridge_source_audit.json | If bridge considered | Source/beamforming provenance. |
| override_log.md | Yes | Any manual decisions. |
| gate0_review_memo.md | Yes | Go/no-go summary. |

## 9.5	8.5 Gate 0 decision states

| State | Meaning | Allowed next step |
| --- | --- | --- |
| metadata_ready_only | Sidecars/events parsed but payloads absent | docs, schemas, synthetic only |
| partial_signal_ready | Some payloads readable | pilot only, no claim |
| signal_ready_no_bridge | EEG/iEEG pass, bridge locked | Gate 1 for RIFT-Net Lite path |
| signal_ready_with_bridge | EEG/iEEG and bridge pass | Gate 1 including optional bridge path |
| blocked | Payload/alignment/cohort fail | Scenario D or data remediation plan |

## 9.6	8.6 Gate 0 review checklist

- ☐ Snapshot path unique.

- ☐ File hashes generated.

- ☐ EDF materialized count > 0.

- ☐ EEG and iEEG read pass for candidate cohort.

- ☐ Event windows valid.

- ☐ Class 4/8 trial counts after QC present.

- ☐ Exclusion reasons present.

- ☐ N_primary_eligible is not public N by default.

- ☐ Bridge is either verified or explicitly locked.

- ☐ No override based on model result.

- ☐ Review memo signed/dated.

# 10	9. Gate 1 SOP: Decision Simulation, SESOI and Influence Governance

## 10.1	9.1 Goal

Gate 1 locks how the study will be interpreted before substantive outcomes are observed.

It converts small-N uncertainty into explicit decision rules:

- SESOI;

- claim thresholds;

- influence ceiling;

- pivot rules;

- power/precision scenarios;

- allowed claim states.

## 10.2	9.2 Inputs

- cohort_lock_signal_ready.json

- Gate 0 review memo

- planned comparator list

- planned controls

- default SESOI values

- simulation configuration

## 10.3	9.3 Default SESOI values

These are provisional defaults and must be finalized in Gate 1 decision memo:

sesoi_defaults:
  delta_BA_vs_best_scalp: 0.03
  CRTG_BA: 0.02_to_0.03
  max_delta_ECE: 0.02
  influence_ceiling: 0.40
  alpha_maxT: 0.05

## 10.4	9.4 Gate 1 steps

- Read N_primary_eligible and valid outer folds.

- Define comparison of interest: RIFT-Net Lite vs best scalp-only comparator.

- Run decision simulation over effect sizes, teacher survival, heterogeneity and influence.

- Lock SESOI and thresholds.

- Lock pivot logic.

- Write decision memo and registries.

- Review and sign off.

## 10.5	9.5 Required outputs

| Output | Content |
| --- | --- |
| decision_memo.md | N_eff, SESOI, thresholds, pivot rules, influence rule. |
| sesoi_registry.yaml | Final SESOI values and rationale. |
| simulation_registry.json | Grid, seeds, assumptions, results. |
| influence_rule.yaml | Formula, threshold, consequence. |
| gate1_review_memo.md | Go/no-go for Gate 2. |

## 10.6	9.6 Gate 1 no-go conditions

- SESOI chosen after seeing model outcomes.

- N_eff missing or inconsistent.

- Influence rule absent.

- Pivot logic absent.

- Decision memo not linked to cohort lock.

- Simulation registry missing seeds/assumptions.

# 11	10. Gate 2 SOP: Synthetic Validation and Threshold Lock

## 11.1	10.1 Goal

Gate 2 proves the pipeline works for the right reason before real-data substantive runs.

Expected behavior:

- True observable teacher helps.

- Non-observable teacher does not create robust gain.

- Nuisance-shared teacher is caught by controls.

- Shuffled labels collapse to chance.

- Shuffled/time-shifted teacher removes privileged gain.

- CRTG statistics detect valid vs pseudo-transfer.

## 11.2	10.2 Synthetic families

| Family | Purpose |
| --- | --- |
| Observable teacher | Positive control: RIFT-Net should recover transfer. |
| Non-observable teacher | Gate should down-weight or block. |
| Nuisance-shared teacher | Controls should detect pseudo-transfer. |
| Spatial shortcut teacher | Spatial controls should detect shortcut. |
| Subject-ID shortcut | Subject probe should detect identity encoding. |
| Null teacher | Model should not invent transfer. |

## 11.3	10.3 Required outputs

| Output | Purpose |
| --- | --- |
| synthetic_generator_spec.json | Generator parameters, dimensions, seeds. |
| synthetic_recovery_report.md | Recovery and failure patterns. |
| gate_threshold_registry.json | Frozen thresholds for controls/gates. |
| toy_control_results.csv | Evidence controls catch confounds. |
| gate2_review_memo.md | Go/no-go for prereg bundle. |

## 11.4	10.4 Gate 2 no-go

- Synthetic true transfer not recovered.

- Nuisance-dominant synthetic passes as valid transfer.

- Shuffled labels above chance.

- Time-shifted teacher retains privileged gain.

- CRTG implementation disagrees with known synthetic truth.

# 12	11. Gate 2.5 SOP: Preregistration Bundle and Release Blocker

## 12.1	11.1 Goal

Gate 2.5 freezes the execution package before real-data substantive runs.

## 12.2	11.2 Required prereg bundle contents

| Item | Required content |
| --- | --- |
| Dataset artifacts | Gate 0 run ID, manifest hash, cohort lock hash. |
| Gate 1 artifacts | decision memo, SESOI, simulation registry. |
| Gate 2 artifacts | synthetic validation, threshold registry. |
| Model configs | RIFT-Net Lite primary config; extension configs marked optional. |
| Baseline configs | bandpower/logistic, Riemannian, EEGNet, EEGNet-TCN. |
| Control configs | C0/C1/C2 tiers, seeds, capacity, adequacy rules. |
| Evaluation configs | CRTG bootstrap, max-T permutation, calibration, influence. |
| Environment lock | Python/packages/hardware/seeds. |
| Revision policy | What can and cannot change after freeze. |

## 12.3	11.3 Gate 2.5 pass condition

{
  "prereg_status": "locked",
  "artifact_hashes_present": true,
  "revision_policy_present": true,
  "environment_lock_present": true,
  "release_blocker_cleared": true
}

If prereg status is not locked, no full real-data claim-bearing run is allowed.

# 13	12. Baseline Execution SOP

## 13.1	12.1 Purpose

Baselines define the scalp-only ceiling and prevent weak-comparator overclaim.

## 13.2	12.2 Baseline families

| Family | Models | Required? |
| --- | --- | --- |
| Classical scalp-only | bandpower logistic/ridge | Yes |
| Covariance geometry | Riemannian tangent classifier | Yes if covariance stable; otherwise report reason |
| Neural scalp-only | EEGNet compact, ShallowConvNet | Yes |
| Temporal neural | EEGNet-TCN | Yes as Mamba fallback comparator |
| Reconstruction | ridge/CCA/PLS scalp-to-iEEG | Track B, not primary claim alone |
| Naive teacher | naive distillation/A4-like | Yes for teacher fragility comparison |

## 13.3	12.3 Baseline artifact checklist

- ☐ baseline_model_cards/

- ☐ baseline_leaderboard.csv

- ☐ baseline_logits.parquet

- ☐ baseline_calibration.json

- ☐ baseline_split_audit.json

- ☐ baseline_leakage_audit.json

## 13.4	12.4 No-go

- Missing strong scalp-only comparator.

- Baseline fit uses outer-test subject.

- Riemannian reference fit across all subjects.

- Calibration fit on outer-test.

- Baseline leaderboard lacks fold-level outputs.

# 14	13. Control Generator SOP

## 14.1	13.1 Purpose

Controls must be deterministic, preregistered and auditable. They are not optional post-hoc checks.

## 14.2	13.2 Required controls

| Control | Required status | Notes |
| --- | --- | --- |
| nuisance_only | Required/blocking | Session/run/trial metadata; capacity preregistered. |
| spatial_permutation | Required/blocking | Deterministic corruption/reversal/permutation. |
| shuffled_teacher | Required | Break teacher correspondence. |
| time_shifted_teacher | Required | Tests temporal/task alignment. |
| subject_id_probe | Required diagnostic | Demote claim if identity encoding high. |
| phase_mismatch | Conditional | Required only if phase trial count adequate. |
| label_shuffle | Required sanity | Must collapse near chance. |

## 14.3	13.3 Control adequacy protocol

A control is adequate only if all required conditions pass:

- capacity tier preregistered;

- seed logged;

- fit scope valid;

- synthetic sanity pass;

- train-fold sanity not broken;

- no outer-test fit;

- output artifact produced;

- adequacy status recorded.

## 14.4	13.4 Control tier capacity config

control_tiers:
  C0_simple:
    model: logistic_regression
    penalty: l2
    C: 1.0
  C1_standard:
    model: shallow_mlp
    hidden_dim: 32
    n_layers: 1
    dropout: 0.25
    max_epochs: 100
    early_stopping_patience: 10
  C2_strong_stress:
    model: capacity_matched_mlp
    hidden_dim: 64
    n_layers: 2
    dropout: 0.35
    use_only_control_valid_inputs: true

## 14.5	13.5 Control artifact fields

control_results.csv must include:

control_id, tier, fold, outer_subject, seed, input_hash, output_hash,
fit_scope, model_capacity, BA_control, AUROC_control,
adequacy_status, adequacy_reason, included_in_max_controls,
required_for_claim, claim_effect

# 15	14. RIFT-Net Lite Training SOP

## 15.1	14.1 Purpose

RIFT-Net Lite tests whether residual anti-teacher learning improves control-robust transfer under scalp-only test-time inference.

## 15.2	14.2 Stage schedule

| Stage | Model/loss | Goal | Exit rule |
| --- | --- | --- | --- |
| Stage 0 | RIFT-0, L_task | Scalp-only sanity | Above chance; label shuffle near chance. |
| Stage 1 | + naive teacher | Test raw teacher usefulness | Report raw BA and controls. |
| Stage 2 | + residual gate | Clean teacher elements | Gate stable, no circularity. |
| Stage 3 | + anti-teacher margin | Reduce pseudo-transfer | CRTG proxy improves without teacher alignment collapse. |
| Stage 4 | + adversarial optional | Suppress nuisance/subject identity | Probe drops without calibration collapse. |
| Stage 5 | + control-margin optional | Fine-tune CRTG | Only after controls stable; never tune on outer-test. |

## 15.3	14.3 Training logs required

- training_log.csv

- grad_norm_log.csv

- teacher_gate_table.csv

- model_card.json

- fold_logits.parquet

- fit_scope_log.json

- stage_transition_report.md

## 15.4	14.4 Stage transition rule

Do not unlock the next stage by epoch count alone. Require:

- current stage artifact complete;

- no leakage policy fail;

- gate circularity tests pass if gate used;

- validation loss/metric stable;

- no gradient norm domination;

- no claim implied from pilot.

# 16	15. Residual Teacher Gate SOP

## 16.1	15.1 Anti-circularity requirement

Gate computation must be detached from task-gradient flow.

Required rules:

- Gate statistics computed on outer-train/inner-validation only.

- Association metrics computed under no_grad or detached.

- Gate weights frozen within each stage.

- Gate recompute only at preregistered stage boundary.

- No gate threshold uses outer-test results.

- Toy gameable gate test must pass.

## 16.2	15.2 Gate versioning

Every gate table must include:

gate_version, gate_fit_scope, gate_recompute_reason,
teacher_id, roi, band, phase, fold, outer_subject,
task_relevance, scalp_observability, stability, residual_cleanliness,
gate_weight, status, failure_reason

## 16.3	15.3 Gate review checklist

- ☐ detached_association=true

- ☐ gate_fit_scope != outer_test

- ☐ gate_version logged

- ☐ blocked teacher elements have reason code

- ☐ teacher survival fraction reported

- ☐ no recompute inside batch loop

# 17	16. Riemannian Branch SOP

## 17.1	16.1 Activation rule

Riemannian branch is optional. Activate only after:

- RIFT-Net Lite baseline exists;

- covariance feature audit pass;

- FoldAwareTangentSpace tests pass;

- trials per class adequate;

- condition number acceptable;

- ablation plan preregistered.

## 17.2	16.2 FoldAwareTangentSpace interface

class FoldAwareTangentSpace:
    def __init__(self, metric="riemann", shrinkage="oas"):
        self.reference_ = None
        self.reference_hash_ = None
        self.fit_subjects_ = None

    def fit(self, covariances, subjects, fold_train_subjects):
        assert set(subjects).issubset(set(fold_train_subjects))
        self.fit_subjects_ = sorted(set(subjects))
        self.reference_ = geometric_mean(covariances)
        self.reference_hash_ = sha256_array(self.reference_)
        return self

    def transform(self, covariances, subjects, fold_id):
        assert self.reference_ is not None
        return tangent_project(covariances, reference=self.reference_)

## 17.3	16.3 Auto-disable reasons

| Reason code | Meaning |
| --- | --- |
| low_trials_per_class | Trial count below locked threshold. |
| unstable_covariance | Condition number too high. |
| reference_fit_scope_invalid | Reference could include outer-test. |
| pca_fit_scope_invalid | Dim reduction fit outside train. |
| no_ablation_gain | Branch adds complexity without value. |

# 18	17. RIFT-Mamba Extension SOP

## 18.1	17.1 Activation rule

RIFT-Mamba is not a default flagship. Activate only after:

- RIFT-Net Lite and EEGNet-TCN results exist;

- Mamba dependency installed and smoke-tested;

- GPU runtime can train one fold within resource limits;

- promotion rule preregistered.

## 18.2	17.2 Promotion rule

promotion_rule:
  delta_BA_min: 0.03
  delta_CRTG_min: 0.02
  require_no_calibration_degradation: true
  require_influence_pass: true
  require_controls_pass: true
  require_subject_probe_pass: true

If RIFT-Mamba fails promotion rule, keep it supplementary.

## 18.3	17.3 Colab fallback

If Mamba causes OOM, unstable kernels or unacceptable runtime:

- stop Mamba run;

- do not rewrite claim;

- fallback to EEGNet-TCN;

- record mamba_runtime_blocked in model card.

# 19	18. RIFT-Bridge SOP

## 19.1	18.1 Activation rule

RIFT-Bridge can be used only if bridge_source_audit.json reports:

{
  "mat_parse_pass": true,
  "subject_mapping_pass": true,
  "session_mapping_pass": true,
  "trial_level_index_verified": true,
  "roi_source_provenance_pass": true
}

## 19.2	18.2 If bridge audit fails

- Lock RIFT-Bridge.

- Use iEEG ROI-band-phase teacher if available.

- Report bridge limitation.

- Do not compute new bridge derivatives unless a separate preregistered supplementary branch is created.

# 20	19. CRTG Evaluation SOP

## 20.1	19.1 Required inputs

- real model logits;

- control logits;

- fold/subject manifest;

- control adequacy table;

- calibration outputs;

- influence outputs.

## 20.2	19.2 Evaluation steps

- Validate all required controls exist or are marked inadequate with claim effect.

- Compute BA/AUROC/ECE by subject/fold.

- Compute max valid control score.

- Compute CRTG per fold/subject.

- Bootstrap subjects 1000 times.

- Run max-T permutation using locked seeds.

- Compute influence concentration.

- Write artifacts.

- Trigger claim-state closeout.

## 20.3	19.3 No-go

- Control results missing.

- Required control inadequate but claim still attempted.

- Bootstrap seed not logged.

- max-T not run but p-value claimed.

- CRTG computed on pooled trials only without subject-level reporting.

# 21	20. Calibration and Influence SOP

## 21.1	20.1 Calibration

Required metrics:

- ECE;

- Brier score;

- NLL;

- reliability curve;

- optional risk-coverage.

Calibration must be fit on inner validation logits only. Do not calibrate on outer-test.

## 21.2	20.2 Influence

Influence concentration:

max_s |Delta_s| / sum_s |Delta_s|

Default threshold: 0.40 unless Gate 1 locks a different value before substantive runs.

Required outputs:

- subject-level delta table;

- top influential fold;

- leave-one-subject-out sensitivity;

- demotion flag if threshold exceeded.

# 22	21. Claim-State Closeout SOP

## 22.1	21.1 Purpose

Claim-state closeout prevents narrative drift. It maps evidence to allowed and forbidden interpretations.

## 22.2	21.2 Closeout decision tree

If Gate 0 not signal-ready -> methodological_only / claim_closed_gate0.
Else if policy test failed -> claim_closed_policy.
Else if required controls missing/inadequate -> inconclusive or claim_closed_control_adequacy.
Else if CRTG CI lower <= 0 -> tentative or inconclusive.
Else if maxT p >= alpha -> tentative or inconclusive.
Else if calibration/influence fail -> demote or close.
Else if artifact complete and no leakage -> claim_allowed.

## 22.3	21.3 Required claim_state.json

{
  "claim_ready": false,
  "claim_state": "claim_closed",
  "claims_opened": [],
  "blocking_reasons": [],
  "allowed_interpretation": [],
  "forbidden_interpretation": [],
  "statistical_support": {},
  "artifact_completeness": {},
  "reviewer_notes": []
}

## 22.4	21.4 Forbidden interpretations by default

- RIFT-Net is SOTA by raw accuracy alone.

- Scalp EEG can replace iEEG.

- iEEG-assisted superiority without controls pass.

- Clinical utility/deployment readiness.

- General scalp-iEEG transfer beyond locked endpoint.

# 23	22. Change Control and Revision Policy

## 23.1	22.1 What can change before Gate 2.5

- draft docs;

- schema names;

- toy tests;

- implementation bugs;

- environment fixes;

- non-substantive formatting.

## 23.2	22.2 What cannot change after Gate 2.5 without new revision

- subject inclusion/exclusion;

- primary split;

- SESOI;

- controls capacity;

- thresholds;

- hyperparameter search space;

- model promotion rule;

- claim-state logic;

- calibration/influence thresholds.

## 23.3	22.3 Revision log fields

revision_id, timestamp, author, artifact_changed, reason,
pre_change_hash, post_change_hash, affects_claim, reviewer, decision

## 23.4	22.4 Emergency patch rule

If a critical bug is found after freeze:

- Stop run.

- Mark artifacts as invalidated.

- Write bug memo.

- Patch code/config.

- Rerun affected tests.

- Create new prereg version if claim-bearing.

- Do not silently patch outputs.

# 24	23. Issue Triage and Escalation

## 24.1	23.1 Severity levels

| Severity | Meaning | Action |
| --- | --- | --- |
| S0 | Claim-invalidating risk | Stop run, fail-closed, lead review. |
| S1 | Gate/policy blocker | Block phase, fix before proceeding. |
| S2 | Reproducibility risk | Fix before full LOSO. |
| S3 | Documentation/clarity issue | Track in revision log. |
| S4 | Cosmetic | Fix opportunistically. |

## 24.2	23.2 Common blockers and responses

| Blocker | Response |
| --- | --- |
| EDF unreadable | Check materialization; if persistent, exclude with reason or block. |
| MAT unreadable | Lock RIFT-Bridge; continue iEEG teacher if eligible. |
| Event alignment fail | Block affected sessions; update cohort lock. |
| Control inadequate | Claim inconclusive/closed; rerun preregistered tier. |
| Gate circularity test fail | Disable gate training and patch before model run. |
| CRTG CI crosses zero | Tentative/inconclusive, not claim allowed. |
| Influence > threshold | Demote strong claim. |
| Outer-test fit detected | Invalidate run. |

# 25	24. Scenario D: Simulation-Only and Data-Readiness Paper Plan

## 25.1	24.1 When Scenario D activates

Scenario D activates when:

- Gate 0 blocked;

- N_primary_eligible too low;

- event alignment fails broadly;

- bridge/iEEG payload unavailable;

- data license/storage prevents materialization.

## 25.2	24.2 Allowed output

No empirical scalp-iEEG transfer claim.

Allowed:

- benchmark specification paper;

- simulation validation paper;

- data-readiness report;

- negative finding about materialization/provenance limitations;

- reusable implementation scaffold.

## 25.3	24.3 Simulation-only study design

Synthetic teacher families:

- observable transfer;

- non-observable teacher;

- nuisance-shared teacher;

- spatial shortcut;

- subject-ID shortcut;

- null teacher.

Claims allowed:

- NOST-Bench can distinguish true vs pseudo-transfer under synthetic ground truth.

- CRTG and controls catch nuisance/spatial/subject shortcuts in simulation.

- Real dataset remains not claim-bearing until signal readiness pass.

# 26	25. Weekly Execution Plan

## 26.1	25.1 Weeks 1-2: Operations freeze and partial Gate 0

Deliverables:

- Operations Annex approved.

- configs/data/snapshot.yaml ready.

- partial materialization sample.

- partial Gate 0 report.

- initial blocker register.

## 26.2	25.2 Weeks 3-6: Full Gate 0 and Gate 1

Deliverables:

- full materialization report;

- signal manifest;

- cohort lock;

- bridge audit;

- decision memo;

- SESOI registry;

- influence rule.

## 26.3	25.3 Weeks 7-10: Gate 2/2.5, baselines and controls skeleton

Deliverables:

- synthetic recovery report;

- threshold registry;

- prereg bundle;

- baseline leaderboard v0;

- deterministic control generators;

- policy tests.

## 26.4	25.4 Weeks 11-16: RIFT-Net Lite and CRTG stats

Deliverables:

- RIFT-0/Naive/Gated/Anti;

- teacher gate table;

- grad norm logs;

- control results;

- CRTG bootstrap and max-T;

- claim-state draft.

## 26.5	25.5 Weeks 17-23: Extensions and robustness

Deliverables:

- RIFT-TCN;

- optional RIFT-Mamba;

- optional Riemannian;

- bridge if verified;

- ablation table;

- calibration/influence reports.

## 26.6	25.6 Weeks 24-28: Reporting and submission package

Deliverables:

- final leaderboard;

- figures/tables;

- claim-state closeout;

- negative finding or positive result narrative;

- manuscript draft;

- reproducibility supplement.

# 27	26. First Implementation Tranche

The first implementation tranche should avoid heavy modeling. It should produce operational evidence.

| Task | Output | Why first |
| --- | --- | --- |
| Partial Gate 0 | partial_gate0_report.md | Determines empirical feasibility. |
| Deterministic control generators | control_seed_manifest.json | CRTG depends on controls. |
| Policy tests skeleton | tests/policy/* | Prevents leakage before modeling. |
| Gate circularity tests | toy_gameable_gate_must_fail | Blocks major methodological risk. |
| CRTG statistics skeleton | crtg_bootstrap.py, maxT_permutation.py | Avoids point-estimate claim. |
| RIFT-Net Lite skeleton | model_card.json | Primary model without Mamba risk. |
| Claim-state v2.1 | claim_state.json schema | Prevents overclaim. |

# 28	27. Review Meetings and Handoffs

## 28.1	27.1 Weekly review agenda

- Current state.

- New artifacts produced.

- Blockers and severity.

- Policy test status.

- Any revision log entries.

- Next go/no-go decision.

- Risks to claim boundary.

## 28.2	27.2 Handoff packet between phases

Every phase handoff must include:

- run ID;

- artifact list;

- config snapshot;

- pass/fail summary;

- blockers;

- owner;

- reviewer;

- allowed next actions.

Template:

handoff_packet:
  phase: gate0
  run_id: ...
  owner: data_governance_lead
  reviewer: scientific_lead
  artifacts:
    - signal_manifest.json
    - cohort_lock_signal_ready.json
  status: signal_ready_no_bridge
  blockers: []
  next_allowed_actions:
    - gate1_decision_simulation
    - baselines_after_gate2_5

# 29	28. Reporting Discipline

## 29.1	28.1 Required tables

| Table | Required content |
| --- | --- |
| Data readiness | N_raw, N_primary_eligible, exclusions, bridge status. |
| Baseline leaderboard | BA, AUROC, ECE, Brier, CRTG if relevant. |
| Controls | BA_control, adequacy, pass/fail, reason. |
| CRTG statistics | median, CI, max-T p, SESOI. |
| Ablations | RIFT-0, Naive, Gated, Anti, Adv, Full, TCN/Mamba. |
| Calibration | ECE/Brier/NLL per model. |
| Influence | subject deltas and influence concentration. |
| Claim-state | allowed and forbidden interpretations. |

## 29.2	28.2 Required figures

- Gate pipeline: Gate 0 -> Gate 1 -> Gate 2 -> Gate 2.5 -> runs.

- NOST-Bench tracks A-E.

- RIFT-Net Lite architecture.

- Residual gate anti-circularity.

- Raw BA vs CRTG leaderboard.

- Control-collapse chart.

- Subject influence plot.

- Claim-state matrix.

## 29.3	28.3 Limitations section must include

- small-N uncertainty;

- strict controls may close positive claim;

- bridge provenance constraints;

- clinical utility not claimed;

- dataset/task specificity;

- Mamba supplementary unless promoted.

# 30	29. Reviewer Defense Notes

## 30.1	29.1 Why not claim by raw accuracy?

Because raw BA can be explained by nuisance/spatial/subject shortcuts. NOST-Bench evaluates transfer validity, not only prediction performance.

## 30.2	29.2 Why controls are strict?

Because if a control explains the gain, the gain cannot be interpreted as genuine scalp-iEEG transfer. Strict controls reduce false-positive claims.

## 30.3	29.3 Why RIFT-Net Lite primary instead of Mamba flagship?

Small-N EEG requires compact, auditable models first. Mamba is tested as an extension and promoted only by ablation.

## 30.4	29.4 Why graded claim states?

Binary pass/fail hides uncertainty. Graded states distinguish strong evidence, tentative evidence, inconclusive controls, control-fragile performance and data-blocked scenarios.

## 30.5	29.5 What if all controls kill the gain?

That is a valid negative finding. The benchmark reveals that apparent transfer is not robust under the locked controls.

# 31	30. Appendices

## 31.1	Appendix A. Minimum policy tests

test_no_outer_test_fit
test_no_ieeg_test_time
test_prereg_required
test_no_posthoc_subject_drop
test_gate_has_no_task_gradient
toy_gameable_gate_must_fail
test_deterministic_controls
test_subject_probe_fit_train_only
test_riemannian_reference_not_fitted_on_outer_test
test_crtg_bootstrap_ci
test_maxT_permutation

## 31.2	Appendix B. Minimal command skeleton

# Gate 0
python -m src.cli nost_gate0_signal --config configs/data/snapshot.yaml --include-signal

# Gate 1
python -m src.cli nost_gate1_decision --gate0-run artifacts/gate0/<run> --config configs/gate1/decision.yaml

# Gate 2
python -m src.cli nost_gate2_synthetic --gate1-run artifacts/gate1/<run> --config configs/gate2/synthetic.yaml

# Gate 2.5
python -m src.cli nost_prereg_assemble --gate2-run artifacts/gate2/<run> --config configs/prereg/assembly.yaml

# Baselines
python -m src.cli nost_run_baselines --prereg artifacts/prereg/<run>/prereg_bundle.json

# Controls
python -m src.cli nost_run_controls --benchmark-run artifacts/baselines/<run>

# RIFT-Net Lite
python -m src.cli nost_train_rift --variant lite --prereg artifacts/prereg/<run>/prereg_bundle.json

# Evaluation
python -m src.cli nost_eval_crtg --controls artifacts/controls/<run> --bootstrap 1000 --permutation 1000

# Closeout
python -m src.cli nost_claim_closeout --eval-run artifacts/evaluation/<run>

## 31.3	Appendix C. Go/No-Go summary

| Gate | Go if | No-go if |
| --- | --- | --- |
| Gate 0 | signal-ready cohort lock | payload/alignment/cohort fail |
| Gate 1 | SESOI and decision memo locked | thresholds missing or post-hoc |
| Gate 2 | synthetic expected patterns pass | nuisance synthetic falsely passes |
| Gate 2.5 | prereg bundle locked | hashes/env/revision policy missing |
| Baselines | strong comparators complete | weak/missing comparator |
| Controls | required controls adequate | underpowered/missing controls |
| RIFT-Net Lite | policy tests pass | gate circularity/leakage |
| Claim closeout | all rules pass | any blocker remains |

## 31.4	Appendix D. Minimal blocker register

blocker_register:
  - blocker_id: B001
    severity: S1
    phase: Gate0
    description: EDF payloads not materialized
    owner: Data Governance Lead
    status: open
    decision: no_claim_bearing_run
    next_action: materialize_subjects_mode

## 31.5	Appendix E. Final operational recommendation

Proceed in this order:

- Freeze Operations Annex.

- Run partial Gate 0.

- Implement policy tests and deterministic controls.

- Lock Gate 1 decision rules.

- Pass Gate 2 synthetic validation.

- Assemble Gate 2.5 prereg bundle.

- Run baselines.

- Run RIFT-Net Lite.

- Run CRTG statistics and claim-state closeout.

- Only then consider RIFT-Mamba, Riemannian and Bridge extensions.

Do not skip gates to reach a positive model result faster. The value of NOST-Bench is that it makes invalid positive claims hard to produce.